## ALLSTATE
FISCAL YEAR 2012-2013 STARTING BALANCE $82,156.01
PRIORITY | ITEM ID | ITEM | ESTIMATED COST | SPENT TO DATE | EST. COST REMAINING | PROJECT TYPE | DETAILED DESCRIPTION | STATUS | SCHEDULE/COMMENTS
1 | 13-9A | Fire Training Center - Add 2 Portables | 30000 | 6204.83 | 23795.17 | New | Portables have been moved. Meeting to be scheduled with Jim Terry, JC Brock, Vivian & Scott | In Progress | 2 Portables being moved from CL
2 | 13-9B | Fire Training Center - Running Track | TBD |  |  | Repair | Possible Home Depot Grant. JC Brock to advise James Pedicone when meeting scheduled. | TBD
3 | 13-9C | 2nd Floor Conference Rm - Wall Removal | 250 | 217.55 | 32.45 | Renovation | Remove wall to enlarge conference Room. Scott to review and provide estimate. | Completed | Completed
4 | 13-9D | Florida Room - Lighting | 5527 | 0 | 5527 | Upgrade | Request additional lighting for the stage area to enhance the environment for special events and video presentations. | In Progress | Scott waiting for permit approval. Need to be completed by 5/31
5 | 13-9E | AC200 - Wallpaper Removal & Paint | TBD | N/A | N/A | Repair | To be done by Maintenance | Completed | TBD
6 | 13-9F | For 113 - 4 Bariatric Chairs conference chars and 4 bariatric side chairs, for Business Office 2 desk chairs and 2 student computer chairs For Kathi Brown - 1 desk chair | 6500 | 6383.78 | 116.22 | New | Business Office & Katie Brown. Vivian to order | Completed | Delivered 6/21/13
7 | 13-9G | Cameras for Security | TBD |  |  | New | Dave Downen to provide cost | Completed | Completed
8 | 13-9H | Rm 206 (Kitchen) - Instant hot water & power | 750 | 241.21 | 508.79 | New | Scott Weaver to submit permit request to Randy
9 | 13-9I | Egress Maps | TBD |  |  | Update | Vivian to send floor plans to Geof Brown for identification of primary & secondary routes
10 | 13-9J | Carpet - Rms 209,210,217,221,222, balance of 100 | 39096.21 | 39096.21 | 0 | Replace | Quote submitted, PO in process | in Process
Other | 13-9K | Skid Pad Replacement | TBD | N/A | N/A | Repair | May be able to fund with lab fees. Estimated Cost $49,750.00 | On Hold | On Hold
Other | 13-9L | Renovate Restrooms | Other Furnding | N/A | N/A | Renovation | Will need to be part of a larger project | On Hold | N/A
Ongoing | 13-9Misc | Miscellaneous Items |  |  |  | Ongoing
Ongoing | 13-9Trav | Travel | 500 | 41.39 | 458.61 | Ongoing
|  | AC TOTALS | 82623.21 | 52184.97 | 30438.24 | NOTE: Estimated Cost Remaining is difference of Estimated Cost and Spent to Date
|  | AC FUNDS NOT COMMITTED | -467.2 | N/A | N/A
|  | AC FUNDS REMAINING TO DATE | N/A | 29971.04 | N/A
FISCAL YEAR 2011-2012 COMPLETED PROJECTS
PRIORITY |  | ITEM | ESTIMATED COST | SPENT TO DATE | EST. COST REMAINING | PROJECT TYPE | DETAILED DESCRIPTION | STATUS | SCHEDULE/COMMENTS
Completed |  | Wall Repair - Defensive Tactics Room | 20679.75 | 4584.29 |  | Repair | Repair and Reinforce damaged walls in the Defensive Tactics Room | Completed | Completed
Completed |  | New Exterior Signage | N/A | n/a |  | Replacement | New exterior signage to replace existing worn and damaged signs | Completed | Completed
Completed |  | Exterior Signage | 325 | 325 |  | New | Add logo to back of one of the new signs | Completed | Completed
Completed |  | Casework & Carpet - Student Registration | 17700 | 9621.56 |  | Renovation | Renovate counter in Business Office for the placement of the student registration computers. Cut-down & relaminate table in breakroom | Completed | Completed
Completed |  | Rm 228 - Brian Frank | 1350 | 1313.14 |  | Renovation | Renovate conference room for Brian Frank's office | Completed | Completed
|  | TOTAL COSTS | 40054.75 | 15843.99 | 24210.76 |  |  |  | SPENT 2011-2012 (MATERIAL ONLY)
REMAINING BALANCE 2011-12 ROLLED OVER TO 2012-13

## CLW
FISCAL YEAR 2012-2013 STARTING BALANCE $214,886.53
PRIORITY | Item ID | ITEM | ESTIMATED COST | SPENT TO DATE | EST. COST REMAINING | DETAILED DESCRIPTION | STATUS | SCHEDULE COMMENTS
1 | 13-2N | Close in office, AD 118 | 1350 | 206 | 1144 | Add 2 doors, locksets and a window to office area currently with a pass-thru | In Progress | approved, In-House Const. working on
2 | 13-2C | Arts Auditorium - Sound Platform | TBD |  |  | Remove three rows of auditorium seat and creat platform for sound equipment at the back of auditorium | pending | by Fall if possible
4 | 13-2O | NM lobby kiosk | 9000 | 0 | 9000 | add smart flat screen kiosk for James Miller Collection to 2nd floor lobby | quoting | request by Mike Stumpe, Stan reviewing
5 | 13-2P | NM 166 re-configuration |  |  |  | former technology lab repurposing for College of Ed |  | request from Pat Roper, as per Stan: no cabinetry removal or significant work
6 | 13-2I | Repurpose Hard Drive Café for Office | 0 |  |  | Currently the Communcations Program Office in the LA Bldg has limited space for the department chair to work with students or faculty. This remodel will enhance the function of this program. | Hold | Hold as per Dr. Vittetoe
7 | 13-2L | Purchase student seating, paint lobby of LA building | 18000 | 15001.06 | 2998.94 | furniture $13, 261.06. Need estimates on painting | In Progress | approved, ordering furniture
8 | 13-2Q | Carpet, furniture, and equip LA 112 | 33000 | 16571.68 | 16428.32 | Requested by Matthew Bodie, furn $12,278.26, carpet $2,370, equip $1606.18 | quoting | pricing phase
10 | 13-2S | Move equipment to photo lab, CR |  |  |  | from AC and to go from storage to CR | quoting | Construction pricing up
11 | 13-2M | Add bollards for sidewalks | 2500 | 2359 |  | goal is to prevent vehicular traffic from entering quad accidentally | quotes | JS getting quotes
12 | 13-2T | Look into new site signage |  |  |  | Establish cost, plan for updating directories and site signage on quad, etc.
Complete | 13-2K | SS104 - Relocate Staff | 5000 | 3975.46 | 1024.54 | Relocate staff from portables to SS104 | Complete | Elect/Data & clearing in progress
Complete | 13-2A | Library - West End | 5000 | 0 | 5000 | Removal of shelving and additional electrical | Complete | Furniture moved. Electrical done.
Complete | 13-2J | BT Classroom Furniture | 100000 | 87550.45 | 12449.55 | Request whiteboards, ELMOs,& updated furniture for the College of Business | Complete | Work done prior to winter break.
Completed | Rollover | LED Sign for Quad | 20660 | 20660 | 0 |  | Complete | Rolled over from 2011-12 FY
Ongoing | 13-2Misc | Miscellaneous Items | 7500 | 6676 | 824 | privacy fencing | Ongoing
Ongoing | 13-2Trav | Travel | 500 | 430.77 | 69.23 |  | Ongoing | N/A
|  | CL TOTALS | 202510 | 153430.42 | 48938.58 | NOTE: Estimated Cost Remaining is difference of Estimated Cost and Spent to Date
|  | CL FUNDS NOT COMMITTED | -8179.33 | N/A | N/A
|  | CL FUNDS REMAINING TO DATE | N/A | 61456.11 | N/A
FISCAL YEAR 2011-2012 COMPLETED PROJECTS
PRIORITY |  | ITEM | ESTIMATED COST | SPENT TO DATE | EST. COST REMAINING | DETAILED DESCRIPTION | STATUS | SCHEDULE COMMENTS
Completed |  | Writing Studio | Other Funding | N/A |  | Renovation of space in the library to create a writing studio that includes furniture, & Mediascape system. Additional items have been added to the original scope. | Complete | Completed
Completed |  | Program Office for 4-Yr Biology | 2500 | 1107.41 |  | Make the necessary modifications to SS 177 to serve as Program Office for the 4-Year biology program by creating an office w/posible staff or student assitant space | Complete | Completed
Completed |  | Student Activities Carpet | 15753 | 15753 |  | New carpet/paint for the Student Activities Area | Completed | Completed
Completed |  | AD Bldg Upgrades | 39600 | 33800.41 |  | Furniture, Paint & Base Completed. Floor Mats on Order | Complete | Completed
Completed |  | NM220-Upgrades | 22000 | 13616.35 |  | Furniture, projector, sink, and instructor's station to upgrade classroom. | Complete | Completed
Completed |  | Add power to desks in LA151 | 22000 | 11835.8 |  | Add power to desks in LA-151. this tiered classroom is often used for the IDS program in which classes last for hours. The charging of laptops is an issue | Complete | Completed
Completed |  | Security Cameras | 20879.66 | 15990.66 |  |  | Complete | Completed
Completed |  | Mock Courtroom | TBD | 571.2 |  | Additional Technology for Mock Courtroom | Complete | Completed
Completed |  | Sign Language Program | 277.32 | 288.22 |  | Project Screen Parts & Holders | Complete | Completed
Ongoing |  | Travel | Ongoing | 46.28 |  |  | Ongoing | N/A
|  | Total Estimated Costs FY 2011-12 | 123009.98 | 93009.33 | 30000.65

## DT-MT
FISCAL YEAR 2012-2013 STARTING BALANCE $68,679.54
PRIORITY | ITEM ID | ITEM | ESTIMATED COST | SPENT TO DATE | EST. COST REMAINING | PROJECT TYPE | DETAILED DESCRIPTION | STATUS | SCHEDULE COMMENTS
1 | 13-15A | Midtown Office for Assoc. Provost | TBD |  |  | New |  | On Hold | Need Dr. Gordon's approval to hire architect to get permit from the city.
2 | 13-15B | Learning Support Rm 255 | 0 |  |  | Reconfigure | Reconfigure Tutor Station in the Learning Support Commons | Complete | Completed by moving existing furniutre
3 | 13-15C | Library - Academic Support Initiative | Other Funding |  |  | Renovation | Academic Learning Space: -Library collections: Book, AV, Periodicals, etc. -Open use computer lab: 30+ seats/computers -Testing: Placement testing room w/computers and space for Disability, Make-Up Testing -30 seat computer lab for Library Instruction & other classroom use | Part of Larger Project ~ Other funding? | Dr. Gordon to follow up with Dr. Cooper & Joe Leopold
4 | 13-15D | Testing Area | 22000 | 21986.79 | 13.21 | Renovation | Add 2 new offices to testing area | Summer | To be completed by July by In-House Construction
5 | 13-15E | Palladium - Wiremold Relocate soundboard | 608.98 | 608.98 | 0 | Upgrade |  | complete
5 | 13-15F | Palladium - Doors | 11000 |  | 11000 | Maintenance | Requisition completed | In Progress
| 13-15G | Office Furniture for new office in Testing | 5000 | [5 empty] | Vivian to order to match existing
Ongoing | 13-15Misc | Miscellaneous Items | TBD |  |  |  |  | Ongoing
Ongoing | 13-15Trav | Travel | 500 | 36.05 | 463.95
|  | DT/MT TOTALS | 39108.98 | 22631.82 | 16477.16 | NOTE: Estimated Cost Remaining is difference of Estimated Cost and Spent to Date
|  | DT/MT FUNDS NOT COMMITTED | 29570.56 | N/A | N/A
|  | DT/MT FUNDS REMAINING TO DATE | N/A | 46047.72 | N/A
FISCAL YEAR 2011-2012 COMPLETED PROJECTS
PRIORITY |  | ITEM | ESTIMATED COST | SPENT TO DATE (Materials) |  | Project Type | DETAILED DESCRIPTION | STATUS | SCHEDULE COMMENTS
Completed |  | Computer Stations for Tutoring Lab Rm 314 | 8809.36 | 7552.45 |  | New | Additional Computer Stations needed for Tutoring Labs Rm 314. | Completed | Completed
Completed |  | Furniture for Provost's New Staff Assistant | 3100 | 3073.13 |  | Replace | Furniture for Provost's new staff assistant. | Completed | Completed
Completed |  | Data Card Equipment | 9100 | 8668.71 |  | New | Data Card Equipment for ID System | Completed | Completed
Completed |  | Lockers/Cabinetry for Faculty, Rm 467 | 5500 | 1226.55 |  | New | New Lockers and Cabinetry for Faculty | Completed | Completed
Completed |  | Miscellaneous Items | TBD |  |  | Misc. | Vivian to meet with Provost to identify needs | In Progress | TBD
Completed |  | Miscellaneous Equipment | 6500 | 6017.11 |  | Misc. | 1. DT Security Camera $2,495.00/2. IPAD2 for Admissions, Tutoring, Classrm Instruction, & Student Experience $1,967.00/3. Scanner for Learning Support $335.00/4. Scanner for Student Life/Leadership $335.00/5. Color Printer/Toner for Staff Administration $2,774.44/6. MT Color Printer Fuser $221.99/7. Visio Software for Staff Administration (5 copies) $285.35/8. File Server Backup - 3 units $605.34 9. Server OS Software (4 copies)/10. Repair of Projecter in Rm DC257 | Completed | Completed
Completed |  | Miscellaneous Doors | 700 | 287.51 |  | Replace | Replace 3 Doors | Completed | Completed
Completed |  | Security Camera | 2500 | 2495 |  | New | New Security Camera | Completed | Completed
|  | Total Costs FY 2011-12 | 36209.36 | 29320.46

## EPI
FISCAL YEAR 2012-2013 STARTING BALANCE $66,676.46
PRIORITY | ITEM ID | ITEM | ESTIMATED COST | SPENT TO DATE | EST. COST REMAINING | PROJECT TYPE | DETAILED DESCRIPTION | STATUS | SCHEDULE COMMENTS
1 | 13-1A | D.O. - HR & Tech Training Centers & Offices | 20000 | 18900.19 | 1099.81 | Renovation | Create two staff training centers in Rm 169 and 234. Storage rooms adjacent to 169 to be completely renovated for 2 offices. Will use some exisitng furniture and purchase additional as required. | In Progress | Construction complete. Furniture expected to be delivered at the end of February
2 | 13-1B | D.O. - Dining Room | Other Funding | N/A | N/A | Refurbish | Design Submitted. Waiting for review and approval. | TBD
3 | 13-1C | EpiServices - Space for NTSS | 20000 | 0 | 20000 | Renovation | Renovate Rms 141, 144, & 173 to create one private office, nine workstations, and work areas | In Progress | Items have been cleared and some work has started.
4 | 13-1D | D.O. - Conference Room | Other Funding | N/A | N/A | Update | Charm working design | TBD
5 | 13-1E | D.O. Lobby | Other Funding | N/A | N/A | Maintenance | Removal of wall paper in lobby | Completed | Completed
6 | 13-1F | EpiTech - Collaborative Labs | Other Funding | N/A | N/A | Refresh | Charm to meet with end users to determine scope | TBD
7 | 13-1G | Annex II (JWB) - Folding Tables | 2287.81 | 2287.81 | 0 | Replace | New lighter folding tables requested. Existing ones will be used in D.O. 234 Training Rm and in TS Agora | Completed | Completed
Ongoing | 13-1Misc | Miscellaneous Items | [5 empty] | Ongoing
|  | EPI TOTALS | 42287.81 | 21188 | 21099.81 | NOTE: Estimated Cost Remaining is difference of Estimated Cost and Spent to Date
|  | EPI FUNDS NOT COMMITTED | 24129.85 | N/A | N/A
|  | EPI FUNDS REMAINING TO DATE | N/A | 45488.46 | N/A
FISCAL YEAR 2011-2012 COMPLETED PROJECTS
PRIORITY |  | ITEM | ESTIMATED COST | SPENT TO DATE (MATERIALS) |  | PROJECT TYPE | DETAILED DESCRIPTION | STATUS | SCHEDULE COMMENTS
Completed |  | Central Records Renov. | 4000 | 3255.87 |  | Renovation | Create workstations for two new staff | Complete | Completed
Completed |  | Business Services | 6000 | 3536.47 |  | Renovation | Create office, new carpet, power/data, move staff | Complete | Completed
Completed |  | Institutional Research to EpiTech | 23500 | 18000.05 |  | Move/New | Relocated Institutional Research from EpiServies to EpiTech. | Complete | Completed
Completed |  | Grants Development to EpiSvcs 2nd flr | 3000 | 1816.94 |  | Move | Moved to space that will be vacated by Institutional Research. | Complete | Completed
Completed |  | Veterans Affairs Office | 250 | 229.16 |  | Remodel | Space for two workstations with panel to separate them. | Complete | Completed
Completed |  | DO Security Area | 601.75 | 601.75 |  | Replace | Replaced worn carpet with new | Complete | Completed
Completed |  | D.O. Shared Services Phase 2 | N/A | N/A |  | Renovation | Renovate Baycare Classrooms 176 & 177 for FAS Phase 2 movefrom EpiTech. Renovate old Business Svcs Suite 189 for LMS. Funded by 186 | Complete | Completed
Completed |  | D.O. - Joe Leopold & Asst | 2142.1 | 2142.1 |  | Replace | Replace worn carpet with new | Complete | Completed
|  | TOTAL COSTS FY 2011-12 | 37351.75 | 29582.34

## HEC
FISCAL YEAR 2012-2013 STARTING BALANCE $92,710.63
PRIORITY | ITEM ID | ITEM | ESTIMATED COST | SPENT TO DATE | EST. COST REMAINNG | PROJECT TYPE | DETAILED DESCRIPTION | STATUS | SCHEDULE/COMMENTS
1 | 13-8A | Provost Office | 4500 | 1017.1 | 3482.9 | Renovate | Renovate space to create new office for Dr. Nicotera | Completed | Completed
2 | 13-8B | Lobby Floor Tile | N/A |  |  | Replace | Replace existing tile in the Lobby | On Hold | Waiting for Maintenance Funding
3 | 13-8C | Carpet - 2nd Floor | N/A |  |  | Replace | Replace carpet on the 2nd floor | On Hold | Waiting for Maintenance Funding
4 | 13-8D | Modernize Classrooms | TBD |  |  | Furniture | Replacement of desks with tables in classrooms: HE 105, 177E, 177W, 274A, 274B, 274C, 274D, 212E and 212W. Total Capacity approximately 324 seats. Each room currently accommodates 36 seats. | Phase 1 - Complete Phase 2 - On Hold | Old Baycare furniture installed in classrooms. 274B & D completed w/furniture from CL Portables. Rest on Hold.
FY 12-13 | 13-8E | Library - Carpet |  |  |  | Replace | Replace worn carpet throughout Library space | TBD | Waiting for library funding approval
5 | 13-8E | O & P - Student Lounge | 13000 | 0 | 13000 | Renovate | Build Wall to separate student lounge from office area | TBD | In-house construction to review
6 | 13-8F | Rm 178 - New Desk | 993.64 | 993.64 | 0 | Furniture | New Desk | Completed | Completed
7 | 13-8G | Registration Area - Counter | TBD | ? |  | TBD | New counter for computers in the Registration area. | Completed | Completed
8 | 13-8H | Library NIP & Circulation Desk | TBD | 5.94 | TBD | Renovate | Expand NIP area, add shelving, and rework circulation desk | TBD | Vivian to meet w/Jose & Anne 4/15/13
9 | 13-8I | Physical Therapy - Move beds | 1000 | 1000 | 0 | Study | Structural Analysis complete. Moving physical Therapy beds to the 2nd floor is approved. | In Progress
10 | 13-8J | Thrift Store | TBD |  |  | Renovate | Explore whether lab can go in vacated Thrift Store space | TBD
11 | 13-8K | Portable 608 Removal | TBD |  |  | Remove | Portable to be removed from site | TBD
12 | 13-8L | Dental Hygiene - Chairs | N/A |  |  | Replace | Install new dental chairs w/added electrical | Summer 2013 | On hold until summer
13 | 13-8M | Accessible Restroom on First Floor | N/A |  |  | Renovate | Door openers installed. Looking at renovation of one restrroom near |  | Funding by ADA
14 | 13-8N | BioDex Machine | 639.55 | 639.55 |  | New Equip | Installation of new Biodex machine
TBD | N/A | Restrooms - 2nd Flr | N/A |  |  | Renovate | Renovate 2nd floor restrooms near elevators. | On Hold | ADA or Maint. Fund
TBD | N/A | Enhance Student Intake/Advising/Admin Areas | N/A |  |  | Renovate | Outside of the cafeteria, the student collaboration spaces at HEC are in dire need for a refresh. Students frequently use the main lounge to the left ofmain entrance under the stairs but worn & limited furniture forces some students to sit on the floor when they gather for projects & lunch. The old telephone booth sits there with no use since phone was removed a while ago & the TV that serves this area from a distance is an old tube TV whose picture is dark & grainy. The carpet & silk tree should be replaced. Some pictures &posters were replaced a year ago. Other areas such as the EMS student lounge, advising wait area, & upstairs hallway sitting area have similar needs for updated furniture, carpet, & decor. TVs throughout the building for leisure viewing are all old CRT TVs. | On Hold | $400,000 Estimated Cost. Waiting to determine funding source
Ongoing | 13-8Misc | Miscellaneous Items |  |  |  | Ongoing |  | Ongoing
Ongoing | 13-8Trav | Travel | 500 | 34.06 | 465.94 | Ongoing |  | Ongoing
|  | HEC TOTALS | 20633.19 | 3690.29 | 16948.84 | NOTE: Estimated Cost Remaining is difference of Estimated Cost and Spent to Date
|  | HEC FUNDS NOT COMMITTED | 72077.44 | N/A | N/A
|  | HEC FUNDS REMAINING TO DATE | N/A | 89020.34 | N/A
FISCAL YEAR 2011-2012 COMPLETED PROJECTS
PRIORITY | ITEM ID | ITEM | ESTIMATED COST | SPENT TO DATE | EST. COST REMAINNG | PROJECT TYPE | DETAILED DESCRIPTION | STATUS | SCHEDULE/COMMENTS
Completed |  | Teaching Bunkers | 9000 | 8614.4 |  | Furniture | New Bunkers in Rms 118, 119, 257,258, 208, 209, 262, & 263 | Completed | Completed
Completed |  | Dental HC105 | 5788.28 | 5788.28 |  | Replace | Chairs, Tables, and Blinds for Dental HC105 | Completed | Completed
Completed |  | Lobby Sign | 200 | 198.28 |  | Signage | New multidirectional sign in the main lobby | Completed | Completed
Completed |  | Provost Conference Rm | 3400 | 2931.95 |  | Upgrade | New TV and A/V Upgrades. | Completed | Completed
Completed |  | Front Entry Doors | N/A | n/a |  | Replace | Replace existing front entry doors | Completed | Maintenance Fund
Completed |  | Rm 177 Wall & AV | 20000 | 561.35 |  | Renovate | Remove wall in Rm 177 and rework A/V. Daya working on AV - waiting for estimate | Completed | Completed
Completed |  | 218 & 219 Physical Therapy | 20000 | 15195.11 |  | Renovate | Remove wall between Rms 218 & 219. (Add'l $13,000 for labor not noted in estimated cost) | Completed | Completed
|  | Total Estimated Costs FY 2011-12 | 38388.28 | 33289.37

## SE
FISCAL YEAR 2012-2013 STARTING BALANCE $106,391.82
PRIORITY | ITEM ID | ITEM | ESTIMATED COST | SPENT TO DATE (Materials) | EST. COST REMAINING | PROJECT TYPE | DETAILED DESCRIPTION | STATUS | SCHEDULE/COMMENTS
1 | 13-4A | UP301- Reuph. Conf. Chairs | 1400 | 1381.28 | 18.72 | Update | Reupholster chairs that are faded and worn. | Completed | Completed
2 | 13-4B | Reupholster Chairs - UP 3rd Flr | 3025 | 3024.51 | 0.49 | Update | Reupholster chairs that are faded and worn. | Completed | Completed
3 | 13-4C | UP104 - Advisor (Student Svcs) | 2270 | 2269.35 | 0.65 | New | Furniture/panels to provide privacy for student advising | Completed | Completed
4 | 13-4D | UP - Reupholster Café Chairs | 4500 | 4493.01 | 6.99 | Update | Fabric is over ten years old and worn away. | Completed | Completed
5 | 13-4E | UP-Stand-Up Computer Stations | 2000 | 0 | 2000 | New | Cabinetshop to build stand-up counter for additional computers as well as a printer stand. | Completed | Completed
6 | 13-4F | Info Kiosk - TL & CC Entrances | 750 | 32 | 718 | New | Two new information kiosks like the ones in UPC to be fabricated by Cabinetshop. | Completed | Completed
7 | 13-4G | UP Elevator - Replace Flooring | 0 | 0 | 0 | Replace | Maintenance may have carpet tiles from original project that can be used to replace exisiting | Completed | Completed
8 | 13-4H | LI - Lobby & Back Corridor Seating | 12000 | 1795.44 | 10204.56 | New | Café seats were reupholstered and furniture was relocated to the lobby and classroom corridor. Literature holders for lobby. Order for new items not needed. | Completed | Completed
9 | 13-4I | UP - Student Lounge | Other Funding /TBD | N/A | N/A | New | Convert Collaborative Commons into a larger student lounge, giving Student Life & Leadership more space for meetings and working. Most furniture existing. Some construction needed. Student Activities funding. | In Progress | Most items completed. Art to be installed by July 1
10 | 13-4J | Library Café to Bookstore | Other Funding | N/A | N/A | Renovate | Convert Library Café to Shelled out space for Barnes & Nobel to create larger campus bookstore | In Progress | Expected completion end of July
11 | 13-4K | UPC Café Expansion | 3775 | 0 | 3775 | Renovate | Cost for Engineering to expand café into bookstore | In Progress | Mechanical design to start
12 | 13-4L | Natural Habitat - New Sidewalk | 32000 | 0 | 32000 | New | New sidewalk extending from the Library to the Natural Habitat Park. The total cost is $64,000 incl. permeable material, which would be shared by Provost, City of SE. Will also need benches, trash cans, & signage | In Progress | Plan to do during summer. Getting quotes on furniture and signage
13 | 13-4M | Outdoor Banners | 1390 | 1390 | 0 | Replace | Additional Outdoor Banners for 113th &102nd | Completed | Completed
14 | 13-4N | Entrepreneurship UP102 | 237.3 | 237.3 | 0 | New | Additional hanging system for business wall | Completed | Completed
15 | 13-4O | TL162 - Science Classroom | 4675.21 | 4675.21 | 0 | New | Additional tables & chairs to allow for 40 students | In Progress | PO Issued
16 | 13-4P | Portables 604, 606, 608 | TBD | 0 | TBD | Replace/New | Move SSS to 606 w/exist furn., 606 classrm, 604 art | In Progress
17 | 13-4Q | Umbrellas for outdoor tables | 3830 | 3830 | 0 | New | Umbrellas for tables that are not covered (N. of TL) | Received | Facilities to install
18 | 13-4R | UP Artway | 3000 | 383.17 | 2616.83 | New | Create Art Gallery in UP corridor. Requires Paint & Track Lighting | In Progress | Paint has been purchased
Ongoing | 13-4Misc | Miscellaneous Items |  |  |  | Ongoing |  | Ongoing
Ongoing | 13-4Trav | Travel | 500 | 439 | 61 | Ongoing |  | Ongoing
|  | SE TOTALS | 75352.51 | 23950.27 | 51402.24 | NOTE: Estimated Cost Remaining is difference of Estimated Cost and Spent to Date
|  | SE FUNDS NOT COMMITTED | 31039.31 | N/A | N/A
|  | SE FUNDS REMAINING TO DATE | N/A | 82441.55 | N/A
FISCAL YEAR 2011-2012 COMPLETED PROJECTS
PRIORITY |  | ITEM | ESTIMATED COST | SPENT TO DATE |  | PROJECT TYPE | DETAILED DESCRIPTION | STATUS | SCHEDULE COMMENTS
Completed |  | TL Commons-Reupholstery | 16133.67 | 16133.67 |  | Reupholster | TL104 - Reupholster chairs in the Learning commons | Completed | Completed
Completed |  | Remodel/Create Digital Arts Editing Suite | 30000 | 28007.31 |  | Remodel/ New | Remodel closet for sound-proof editing, furniture, & technology to create a Video Editing Suite | Completed | Completed
Completed |  | Student Services Info Desk | 1075 | 573.79 |  | New | UPC- New Information Desk, signage, and paint | Completed | Completed
Completed |  | Third Floor Staff Assistant | 1000 | 893.88 |  | Reconfigure Moves | UPC - Minor moves and reconfiguring of existing cubicle panels. Minimal cost. | Completed | Completed
Completed |  | The Entrepreneurship "Student Success” Project | 3650 | 3105.32 |  | New | New lighting & signage for "Mind Your Business Wall" outside the Career & Entrepreneurship Ctr | Completed | Completed
Completed |  | Lecterns | 1154.34 | 1154.34 |  | New | Lecterns for Speech Classes | Completed | Completed
Completed |  | Student Support Center-PB608 | 4200 | 4114.67 |  | New | Furniture for SSC's Collaborative Space | Completed | Completed
Completed |  | PB609-Vets Services | 750 | 743.54 |  | Update | New blinds & Replace old furniture& signage | Completed | Completed
Completed |  | TL106 - Office Adjustment | 1600 | 1139.41 |  | Remodel | Remove cabinets, repair carpet, paint, & new desk to improve function | Completed | Completed
Completed |  | New Carpet: PB605 & PB606 | 7200 | 6955.73 |  | Replace | Replace worn and damaged carpet. | Completed | Completed
Completed |  | PB601 - Floor Repair | Other Funding | n/a |  | Repair | $15,000 Estimated cost - other funding source. Portable floor has moisture damage and has to be repaired. This will involve moving out of 6 faculty and new carpet. | Completed | Completed
Completed |  | PB601 - Network Upgrade | 1000 | 0 |  | Upgrade | Network in the portable needs to be updated. Will need to install ventilated cabinet & reconfigure faculty layout. | Completed | Completed
Completed |  | UP102/104 - Career and Entrepreneurship Center | 10000 | 9705.03 |  | New | New mobile furniture in UP102 to collaborate, meet with advisors, teleconference, & class space | Completed | Completed
Completed |  | UP-Reupholster Faded Chairs | 9350 | 9313.3 |  | Reupholster | Reupholster seating that is worn and faded. | Completed | Completed
Completed |  | Renovate TL 120-121 | 20000 | 17131.08 |  | Renovation | TL120 renovated to accommodate 4 new faculty. Incl new furn & electrical closet. | Completed | Completed
Completed |  | Digitorium - Projector Installation | 8000 | 7220.13 |  | Upgrade | Specialized installation required for new upgraded projectors to produce a video wall | Completed | Doug approved adding $4000 from Epi funds to do this project.
Completed |  | PB608 - Student Support Ctr | 1352.96 | 1352.96 |  | New | New storage cabinets to store donation items. | Completed | Completed
FY2011-12 |  | Travel |  | 64.02 |  | N/A |  | Completed | N/A
|  | Total Costs FY 2011-12 | 115113.01 | 107608.18

## SPG
FISCAL YEAR 2012-2013 STARTING BALANCE $260,103.60
PRIORITY | Item ID | ITEM | ESTIMATED COST | SPENT TO DATE | EST. COST REMAINING | PROJECT TYPE | DETAILED DESCRIPTION | STATUS | SCHEDULE/COMMENT
1 | 13-3A | Creating synergies between Learning Support Commons and Library for enhanced out-of-class support | Other Funding | N/A | N/A | Repurpose | During summer, 2012, KKW and Joe Leopold were charged with presenting more extensive, all-encompassing options to Dr. Law and Dr. Cooper, based on cross-campus input. Task Force appointed. This obvioulsy can't be funded solely from Provost discretionary funds, but is still listed here for prioritizing purposes, in line with the college's focus on out-of-class support for our students. | Phase 1 Complete | PHASE 1: Library 2nd floor. Completed. PHASE 2: SP/G Task Force has submitted recommendation for SP/G out of class support "hub."
2 | 13-3B | TE106, 108, 110 - College of Business: Furniture | 2500 | 1677.22 | 822.78 | New | (3) High Back Instructor Stools and (1) Lectern for Classrooms TE106, TE108, & TE110. Need high back/bar height stools the faculty can use in these rooms to lecture from & to be correct height for bunkers. Exisitng ones are standard chairs and thre are none in surplus. Lectern is for one classroom that does not have one | Complete
3 | 13-3C | Math Classrooms - SA 2nd & 3rd Floors | 37549.6 | 37549.6 | 0 | Improve | Replace all tablet desks with tables and chairs; replace any remaining blackboards with white boards. | Complete
4 | 13-3D | Natural Sci: Chemical Waste & Biohazard Rooms upgrades. SC112 and SC110 | 2185.82 | 2185.82 | 0 | Upgrade | Room 112 - Chem Waste Rm: with the number of labs running, shelves are needed to store waste until pick-up. Room 110 - Replace vinyl floor | In Progress | Room 112 - Purchase order issued for shelving Room 110 - purchase order issued for vinyl floor
5 | 13-3E | SC 116 - Water Source | 3000 | 2848.75 | 151.25 | New | Water source (sink & cabinet) needed for undergraduate research | In Progress | Sink & cabinet ordered from Science Equipment Supplier. Construction crew to install when it arrives
6 | 13-3F | AD/Testing Ctr Lockers | 1040 | 1040 | 0 | New | Lockers for students | complete
7 | 13-3G | SC 111 - Storage/Cabinet | 7482.06 | 7482.06 | 0 | New | Storage (shelving) needed for rocks | complete
8 | 13-3H | SC 102, 206, 208 | Cost incl. w/13-3G | N/A | N/A | New | Base cabinets with countertops & overhead shelves to replace carrels. Move existing data & power to 42" AFF | complete
9 | 13-3I | SC 206A | Cost incl. w/13-3G | N/A | N/A | New | Overhead Shelving above existing cabinet | complete
PRIORITY |  | ITEM | ESTIMATED COST | SPENT TO DATE | EST. COST REMAINING | PROJECT TYPE | DETAILED DESCRIPTION | STATUS | SCHEDULE COMMENT
10 | 13-3J | MIRA | 20000 | 18791.91 | 1208.09 | Enhance | Reconfigure south room of MIRA building to accommodate the mixing room and handle the increasing needs of the production program. This involves removing existing cabinetry, installing a window in a stud wall of the recording space, power, network, sound treatment, and monitoring. The current mixing room would be used as an iso-booth for recording. | In progress | Work began 5/6/13. To be completed Summer Session. Not to exceed $25,000
11 | 13-3K | College of Education - TE101 | 100 | 0 | 100 | Enhance | Classroom storage and other furnishings were requested so that the room can continue to be used as a classroom, and also used to store manipulatives and resources for teacher education candidates, so that they can gather and work on projects in between classes. Determined that adding locks to existing cabinetry fulfills this need | complete
12 | 13-3L | TE - Creation of computer lab for specialized use | TBD | 0 | TBD | New | Combine 2 smaller computer labs in TE (TE 228 and 230) into one larger lab, for purpose of additional proctored online testing, and for SP/G Faculty to use on a reservation basis for tests/exams for their F2F classes. | On hold for now.
13 | 13-3M | AD - Testing Center Computer Tables | 20000 | 0 | 20000 | Replace/ Enhance | 26 Replacement computer desks/chairs and 4 additional non-computer desk with chairs, all of a more compact design in order to allow students to walk down aisles without diruption to other students engaged in testing. | In Progress | Quote forthcoming for new tables and chairs
14 | 13-3N | "Student Tech Room" for Music programs - TE 139. (TE 139 will then be a shared space: student tech room and MIRA TSS office.) | 0 | 0 | 0 | New | Tech Room for student work sessions associated with MIRA Audio Engineering and Production classes, furnished with storage cabinets and furniture suitable for students' use of soldering irons, cabling, and other materials used in the repair of recording equipment, studio wiring and other audio electronics projects. | complete | utilized existing furniture from warehouse
15 | 13-3O | SC 1st & 2nd floor | 12000 | 0 | 12000 | New | Students study in hallways; suitable furnture and sound panels needed. | Estimating in progress. | 30" of clear space. Vivian getting quotes
16 | 13-3R | HS 109 Acoustics | 10000 | 0 | 10000 | Upgrade | Acoustical treatment for HS109 (Band Room). |  | Nancy Smith is working with staff to suggest a solution. Cost of Engineer would be $6,000.
17 | 13-3S | Music Center - Sound Booth Relocation | TBD | 0 | TBD | Re-purposing | AD Music Center - Relocate sound booth to rear center of the venue; install ProTools venue system and related equipment, thereby equipping the Music Center as an enhanced venue with student instruction capability as well.This item needs to be considered in consultation with Dean Steele and others regarding other possible Music Center upgrades. | On hold for now.
PRIORITY |  | ITEM | ESTIMATED COST | SPENT TO DATE | EST. COST REMAINING | PROJECT TYPE | DETAILED DESCRIPTION | STATUS | SCHEDULE COMMENTS
18 | 13-3T | SA Building: Hallway Seating | 5000 | 0 | 5000 | New | Seating in South Hallway, 1st floor. Students gather here and appropriate seating is needed. Will need retractable seating because of width of corridor. | In Progress | Estimating in progress
19 | 13-3W | Library - Teen Room | 15000 | 0 | 15000 | Replace | Renovation of Teen Room - Upholstery and furnishings are damaged and in need of repair or replacement | TBD | Design Approved. Waiting for furniture quote.
20 | 13-3X | Administration Bldg Carpet & ceiling replacement in corridor | 21052.68 | 21052.68 | 0 | Replace | Carpet corridors of Administration Building & replace ceiling tiles |  | scheduled for summer 2013
| 13-3Y | Student Support Services - 9 chairs for George Carbarts Area | 3000 | 0 | 3000 | New | 9 chairs needed for Student Support Services |  | Vivian to meet with George and order
Other | N/A | Library: Children's Area Furniture | Other Funding | N/A | N/A | Replace | Friends of the Library is funding new furniture to replace worn. | Complete | Completed
Other | N/A | Gym: volleyball Locker Room | Other Funding | 0 | 0 | Repurpose | Adding lockers and carpet to dressing area; Athletics to fund. | In Progress
Other | N/A | Gym: laundry room | Other Funding | 0 | N/A | Replace | Current equipment more than 15 years old and in need of replacement - 2 washers and 2 dryers. Athletics to fund. | complete
Ongoing | 13-3Misc | Miscellaneous | TBD |  | TBD | Replace and New | Misc needs: | Ongoing
| 13-3Misc | Misc1 - Registration chairs | 1600.25 | 1600.25 | 0 |  | 1) Add high back chairs for students to 7 Advisor stations in Registration Center | complete
| 13-3Misc | Misc2 -CCIT Reupholster | 639.5 | 639.5 | 0 |  | 2) reupholster chairs in CCIT conference room | complete
| 13-3Misc | Misc3 - Carpet in HS110 & HS112 | 3000 | 2994 | 6 |  | 3) Carpet in HS110 & HS112 | complete
| 13-3Misc | Misc4 - Shelving | n/a | 0 | N/A |  | 4) Shelving in storage/equipment room behind sound | complete | created with existing resources
| 13-3Misc | Misc5 - AD107 - Carpet | 1983.05 | 1983.05 | 0 |  | 5) Replace carpet in AD 107 | In Progress | to be done summer 2013
| 13-3Misc | Misc6 - TE - Carpet Stairs | 4837.5 | 4837.5 | 0 |  | 6) Carpet stairs in TE | In Progress | to be done summer 2013
| 13-3Misc | Misc7 - TE Lobby - Carpet | 20655.93 | 20655.93 | 0 |  | 7) Carpet TE Lobby 1st & 2nd floors | In Progress | to be done summer 2013
| 13-3Misc | Misc8 - Fans in Wellness | N/A | 0 | N/A |  | 8) Installation of fans in wellness center (installation only) |  | Fans to paid by Science/Wellness
| 13-3Misc | Misc9 - Paint Wellness Ctr | 3430 | 3430 | 0 |  | 9) Paint Wellnees Center interior |  | Gary getting quote - to be done summer 2013
| 13-3Misc | Misc10 - Ethics Carpet 2nd floor corridor & stairs | 5273.53 | 5273.53 | 0 |  | 10) Replace vinyl tile in Ethics 2nd floor corridors with carpet and install carpet on stairs | In Progress | to be done summer 2013
PRIORITY |  | ITEM | ESTIMATED COST | SPENT TO DATE |  | PROJECT TYPE | DETAILED DESCRIPTION | STATUS | SCHEDULE COMMENTS
| 13-3Misc | Misc11 - Veteran's Office | 200 | 0 | 200 |  | 11) high table for Veteran's Office | In Progress | to be completed by July 1
| 13-3Misc | Misc12 - Repair Circulation Desk where damaged at toespace | 100 | 0 | 100 |  | repair circulation desk damage | In Progress
| 13-3Misc | Misc13 - Podium | 296.24 | 296.24 | 0 |  | Podiums
| 13-3Misc | Misc14 - Where are you going? Poster | 158.75 | 158.75 | 0 |  | Frame Poster for Provost Office
Ongoing | 13-3Sign | Campuswide Interior Signage | N/A | n/a | N/A | On-going | On-going | Ongoing | In progress / ongoing
Ongoing | 13-3Trav | Travel | 500 | 84.56 | 415.44 | N/A |  | Ongoing | N/A
|  | SP TOTALS | 202584.91 | 134581.35 | 68003.56
|  | SP 12-13 FUNDS NOT COMMITTED | 56159.48 | N/A | N/A
|  | SP 12-13 FUNDS REMAINING TO DATE | N/A | 177519.55 | N/A
FISCAL YEAR 2011-2012 COMPLETED PROJECTS
PRIORITY |  | ITEM | ESTIMATED COST | SPENT TO DATE | EST. COST REMAINING | PROJECT TYPE | DETAILED DESCRIPTION | STATUS | SCHEDULE COMMENTS
Completed |  | AD-107 for F2F Orientation: minor improvements | 13500 | 11418.92 |  | Improve | This dedicated room is working very well for F2F orientations. System for power cords needs to be adjusted; would like to explore other minor cosmetic improvements if budget allows. Cosmetic improvements part of this item is further down the priority list. Worked with Tyrone to find best time for their schedule. | Completed | Completed
Completed |  | HUM & FA - MIRA Labs: 12 Workstations | 10000 | 4596.8 |  | New | Assemble & install forthcoming 12 Sterling Modular workstations in HS 120, add power, align network drops as needed. Workstations for keyboards and computers. | Completed | Completed
Completed |  | HUM Rm 116 New Carpet | 1480 | 1480 |  | New | New Carpet for Humanities 116. Move existing HS 120 furniture to HS 116, and install carpet in HS 116 | Completed | Completed
Completed |  | Natural Sci: Bunkers for SC202 | 0 | 0 |  | New | Request is to place the bunker to the side where there is a table now, rather than in the center of the room. Used one from surplus. | Completed | Completed
Completed |  | Math: My Bridge to Success Program (SA-244) | 52000 | 49397.38 |  | Renovate | SPC was awarded $30,000 as one of 5 colleges in FL with a Course Redesign Grant. The grant did not cover any classroom renovation or technology. The classrooms on the Gibbs campus were designed in 2001 and are in need of an update. By outfitting room SP- SA244 with state of the art technology (computers, SMART boards, etc), collaboration modules, and enhanced cosmetic features, students are given a necessary and vital resource to succeed in MAT 0990 Elementary Algebra My Bridge to Success. Our goal is to hold classes in this room and have it staffed with instructors outside of class time so that students can be fully supported. It will hopefully be a model for other campuses and colleges to follow as we lead the charge nationwide for course redesign. | Completed | Completed
Completed |  | Soc & Beh Sci: Psychology Lab (SA-315) | 1000 | 936.45 |  | New | To augment existing equipment already identified by Dean Smiley for this initiative with appropriate facilities enhancements - these will most likely be minor in nature, in that the room will still be used as a regular classroom as well. PHASE 2: will be a request for more extensive enhancements. | Completed | Completed
FISCAL YEAR 2011-2012 COMPLETED PROJECTS (Cont.)
PRIORITY |  | ITEM | ESTIMATED COST | SPENT TO DATE | EST. COST REMAINING | PROJECT TYPE | DETAILED DESCRIPTION | STATUS | SCHEDULE/COMMENTS
Completed |  | SA137 - Special Svcs Volunteer Program Office Furniture | TBD | 0 |  | New / Replacement | Modernized furniture (matching chairs, full-functioning desks [for 2 staff members], artwork, and circular table) to coordinate with surrounding offices and provide a more inviting feel. Note that going forward, artwork to be identified along with other campus artwork planning and selections. | Completed | Completed
Completed |  | Music Center - Projector Shelf | 250 | 0 |  | New | Cabinetshop to make shelf for projector. | Completed | Completed
Completed |  | Vet's Office | 23.99 | 23.99 |  | New | Frame for Flag | Completed | Completed
Completed |  | TE102 - Interactive Equipment | Other Funding | N/A |  | Upgrade | Built-in interactive equipment for the College of Education classroom. Joint effort between facilities and the District IT folks. | Completed | Completed
Completed |  | Ethics Rm 103 - Carpet | 516 | 516 |  | Replacement | New Carpet for Ethics 103. | Completed | Completed
Completed |  | TE120 - Cabinetry | 300 | 127.68 |  | New | Cabinetry for College of Education for additional storage | Completed | Completed
Completed |  | AD105 - Radio Station | 20000 | 5329.36 |  | Remodel | Tranform exisitng office suite into a radio station, requires construction, signage, & furniture. Equipment funded by SGA from student activities funds. | Completed | Completed
Completed |  | HUM & FA: Acoustical Treatment | 18000 | 15278.25 |  | Upgrade | Acoustical treatment for classrooms HS116, HS120, HS122, & HS124. Vendor recommended GIK Acoustics. Needed for quality of classroom experience | Completed | Completed
Completed |  | MIRA Misc. | 600 | 562.13 |  |  |  | Completed | Completed
Completed |  | Quad Site Furnishings | Other Funding | N/A |  | Furnishings | The Quad is an important part of the student experience at SP/G. We are in need of furnishings - benches, picnic tables, trash cans, etc. for events and informal gathering | Completed | Completed
FY 2011-12 |  | Travel | N/A | 30.48
|  | Total Estimated Costs FY 2011-12 | 117669.99 | 89697.44
FY 2011-12 |  | Travel | N/A | 30.48
|  | Total Estimated Costs FY 2011-12 | 158359.98 | 112532.26

## TS
FISCAL YEAR 2012-2013 STARTING BALANCE $109,573.20
PRIORITY | Item ID | ITEM | ESTIMATED COST | SPENT TO DATE | EST. COST REMAINING | DETAILED DESCRIPTION | STATUS | SCHEDULE/COMMENTS
1 | 13-5A | Lyceum - VCT | 25000 | 25500.31 | -500.31 | Replace aging tile on 1st and 2nd floor of Lyceum. Becaue of age and wear, tile is buckling and creating a potential safety hazard for students, faculty, & staff. | Complete | Completed
2 | 13-5B | Partitions for Advising and Registration area | 33000 | 28613.67 | 4386.33 | This project is to create space for two (2) new generalists and to provide more privacy as requested by students. The additional space would be achieved by removing a wall behind the current space and eliminating one of two archive rooms. The existing advising and registration area which houses the Generalists has an open floor plan and high-volume ceilings. The noise level is disruptive to all students trying to speak with Generalists and students have expressed concerns about their privacy (FERPA and personal) since their conversations with Generalists can be easily overheard in the open computer and waiting area. Adding a partition with transparent panels for clear visibility between the waiting area, open computer area for student use, and the Generalists’ area would cut down tremendously on sound transference. Additional partitions between Generalist stations would allow students an increased sense of privacy, break up the transference of sound, and still maintain a sense of openness. | Complete | Completed
2b | 13-5B | Misc. Registration components | 1500 |  | 1500 | window - Kontodiakos office, panels at "pit", TV stand/planter, screen - AD 143 | soon to install | window - need 2 days, other misc. completed
3 | 13-5C | Repurpose Agora's TRS Space to Veterans and SLL Space | 10000 | 8855.67 | 1144.33 | Currently, the Agora building houses Student Life and Leadership, Veterans Services, Campus Security, and TRS offices. The TRS offices occupy a significant space for three (3) TRS' as well as technology equipment. The draw-down of U.S. Troops in foreign wars is increasing the current and projected number of veterans on campus. By moving the TRS spaces to the currently unoccupied space in the Bilirakis Building East Wing, and by replacing the existing flooring in that space with new carpet will enable more effective use of Agora for: Student Life & Leadership, Student Center, StudentLounge &Vending, Security, Veterans, SGA, PTK, MAX and more need for additional office space for clubs | Complete | Complete except for potential purchase of lounge furniture when funding allows.
4 | 13-5D | Library Learning Resource Upgrades | 23930 | 19791.83 | 4138.17 | Add power and data to sixteen (16) study carrels in "quiet study area" to enable students to plug in their laptops and other portable devices. Add collaborative style seating for Flex Classroom LI-150. Add additional tables and chairs to Quiety Study space and former reference area as well as a new information desk. New whiteboard for LI-152 | Complete | Completed
5 | 13-5K | Add panel to digital sign on US 19 for Bilirakis and WorkNet | TBD | 0 | TBD | cost to add individual panels below the digital display on the large monument site sign on US 19 and Klosterman to identify that Congressman Gus Bilirakis and WorkNet reside at the campus. Would be paid by occupants. | app'vd by Bilirakis, WorkNet in review | Order to be placed as soon as WorkNet determines their interest in the lower panel.
6 | 13-5L | Add door between Beth Goodbread and Misty Berry's offices, BB | 1300 | 570.14 | 729.86 | Goal is to connect the Program Director's office and her support | Complete | Completed
7 | 13-5E | Library Learning Resources Windows | 10000 | 0 | 10000 | Fall 2011, Dr. Law suggested windows be placed in the walls separating the writing studio (FA 154), the communications tutoring room (FA 157), and the learning commons area to enable students and visitors to see that leaning is taking place in the writing studio and the communications tutoring room. | On Hold | Holding
8 | 13-5G | Refresh Faculty Lounge in LY | 12000 | 0 | 12000 | Faculty Lounge in Lyceum is in very poor condition. The furniture, refrigerator, & other appliances are very old. Faculty & academic chairs have requested that the room be refreshed. | TBD | Hold as per Dr. Carney 12/10. Revisit in March/April after other approved project expenses are confirmed.
PRIORITY |  | ITEM | ESTIMATED COST | SPENT TO DATE | EST. COST REMAINING | DETAILED DESCRIPTION | STATUS | SCHEDULE/COMMENTS
9 | 13-5H | Refresh Provost Conference Room in Admin Bldg | 15000 |  | 15000 | Replace old, worn furntiure in the Provost Conference Room with new furniture to update room. | Pending | Hold for FY 2013-14
10 | 13-5I | LRMA Museum Store Revenue Enhancements Initiative | 4150 | 1468.09 | 2681.91 | Physical improvements will contribute to increased revenue generation. These would include the following: Table top (jewelry) display case approx. 3’ tall, but 2’ W x 2’ D with approx. 3 glass shelves and glass front and back. (With lights)2 large floor display cases, glass display on top, closed doors on bottom,approximately 6’ long, 4’ tall, 2’deep (with lights) Estimate on sheets of slat wall material (Olin will install) | Complete
11 | 13-5J | Whiteboard resurfacing | 18121.26 | 18121.26 | 0 |  | Approved | Problems with installation over session break May 6-10, need alternative date
12 | 14-5A | FY 2013-14 Request Writing Lab - Library | 20000 | 0 | 20000 | Additional Furniture for Writing Lab in the "Pit" area of the Library and 28 laptops (Meg Delgado/Jorge Perez) | 2013-14 | Writing lab moved with existing furniture to the pit.on 4/4/13
13 | 14-5B | FY 2013-14 Request AS Environmental Sciences Technology Program | 15000 | 0 | 15000 | Graveling / crushed shells and field stations for Nature Trial to support AS Environmental Sciences Technology Program - Delgado/Wallis/Chapin | 2013-14 | Meg Delgado, Kelli Stickrath to determine best trail, Facilities to get approval from SWFMD
14 | 14-5C | FY 2013-14 Request Place-holder: Campus Safety and Security initiatives | 10000 | 0 | 10000 | Inclusive of items sent to JC Brock in email, and items from February 2013 Faculty Seminar Series To be further Defined | 2013-14
15 | 14-5D | FY 2013-14 Request Ethics Classroom | 13000 | 0 | 13000 | New Furntiure for Ethics Classroom (David Monroe) | 2013-14 | Charm/David Monroe to meet
16 |  | Museum Roof | Other Funding | 0 | 0 | $18,000 Estimate (Maintenance - Diana Wright)
Ongoing | 13-5Misc | Miscellaneous Items |  |  |  |  | Ongoing
Ongoing | 13-5Trav | Travel | 500 | 337.23 | 162.77 |  | Ongoing
|  | TS TOTALS | 212501.26 | 103258.2 | 109243.06
|  | TS FUNDS NOT COMMITTED | -102928.06 | N/A | N/A
|  | TS FUNDS REMAINING TO DATE | N/A | 6315 | N/A
FISCAL YEAR 2011-2012 COMPLETED PROJECTS
PRIORITY |  | ITEM | ESTIMATED COST | SPENT TO DATE |  | DETAILED DESCRIPTION | STATUS | SCHEDULE/COMMENTS
Completed |  | Replace Student Furniture | 14374.21 | 14374.21 |  | Replace torn/re-used furniture in windowed alcoves/hallways of Lyceum Building. Furniture is used by students for transition and studying. | Completed | Completed
Completed |  | LRMA Storage | 38400 | 38400 |  | LRMA Art Storage - Purchase storage units required for storing approximately 400 objects of the Gulf Cost Museum of Art pieces in the LRMA storage vault. | Completed | Completed
Completed |  | Lyceum 258 Computer Lab Furniture | 16000 | 15947.83 |  | Lyceum 258 - New computer stations fore 28 students to improve English composition and to support the Developmental Education Initiative (DEI) Project. Reference 3/17/2011 and 2/14/2011 emails., Drs. Campbell and Smith. (Carpet & Equipment to be funded by YellowSheet) | Completed | Completed
Completed |  | TS Library Changes | 27000 | 26792.97 |  | Move function of English/Writing/Humanities Tutoring to Rm 154. Move Science/Math Tutoring to the back "quiet" area and move Quiet area near Study Rooms. Rm 157 would become a Flex classroom for classes and computer lab/study area. Stacks to be relocated to "Pit" and some of that furniture will be relocated to other areas in the Library. May involve some electric/data, reconfiguring of computer stations, purchase new furniture, and moves. | Completed | Completed
Completed |  | Bunker Moves | 4911.79 | 4911.79 |  | Equipment and labor costs to move (5) Instructor Bunkers in the east wing of the Bilirakis Building. | Completed | Completed
FY2011-12 |  | Travel | 500 | 0 |  |  | Completed | N/A
|  | Total Estimated Costs FY 2011-12 | 101186 | 100426.8